## Construction schedule
CONSTRUCTION SCHEDULE
Project: | Bathroom – Merl
Plan start (Monday): |  | 2026-11-02
Stage / task | Who | Start | End | Days | Status
Strip-out and waste removal | Crew 1 | 2026-11-02 | 2026-11-04 |  | Done
Plumbing | Plumber | 2026-11-05 | 2026-11-10 |  | In progress
Electrical installation | Electrician | 2026-11-05 | 2026-11-09 |  | In progress
Waterproofing | Crew 1 | 2026-11-11 | 2026-11-12 |  | Planned
Tiling | Tiler | 2026-11-13 | 2026-11-23 |  | Planned
Sanitaryware and taps | Plumber | 2026-11-24 | 2026-11-25 |  | Planned
Ceiling painting | Painter | 2026-11-24 | 2026-11-25 |  | Planned
Final clean and handover | Crew 1 | 2026-11-26 | 2026-11-26 |  | Planned
Enter start and end dates: the calendar bars colour themselves. Made at adbooks.co